## PM Checklist
PROJECT MANAGEMENT QUICK CHECKLIST
Use this sheet to track completion of each project management step during your project. ¦ Project: Happy Link Claude TLDR Ticket Summary ¦ Owner: Ashley Alayon
Step # | Phase | Step Name | What to Do | Initiated | Last Updated | Status | Completed
1.1 | INITIATE | Identify the Project | Recognized need to speed up HappyFox ticket review by agents; identified opportunity to build a Claude-powered TLDR tool. | May 22, 2026 | May 22, 2026 | Completed | May 22, 2026
1.2 | INITIATE | Define the Project Purpose | Build a Streamlit app (localhost:8501) that auto-summarizes HappyFox support tickets for faster agent review using Claude AI. | May 22, 2026 | May 22, 2026 | Completed | May 22, 2026
1.3 | INITIATE | Identify the Sponsor | Ashley Alayon — Project Owner and lead developer via Claude Code. | May 22, 2026 | May 22, 2026 | Completed | May 22, 2026
1.4 | INITIATE | Clarify Scope & Boundaries | IN SCOPE: HappyFox ticket summarization, Streamlit UI, Claude API integration. OUT OF SCOPE: Full CRM replacement, external user access. | May 22, 2026 | May 22, 2026 | Completed | May 22, 2026
1.5 | INITIATE | Identify Stakeholders | Ashley (PM/Dev), Support Agents (end users), HappyFox (data source), Linksys Ops team. | May 22, 2026 | May 22, 2026 | Completed | May 22, 2026
1.6 | INITIATE | Define Success Criteria | App displays ticket TLDR summaries accurately; agents can review tickets faster; app runs reliably on localhost:8501. | May 22, 2026 | May 22, 2026 | Completed | May 22, 2026
1.7 | INITIATE | Create Project Charter | Project pinned in Claude Code as 'Happy Link Claude TLDR Ticket Summary'; purpose and scope documented in conversation history. | May 22, 2026 | May 25, 2026 | Completed | May 25, 2026
2.1 | PLAN | Build the Work Breakdown Structure (WBS) | Decomposed into: UI design, HappyFox API integration, Claude summarization logic, table/display formatting, bug fixes. | May 22, 2026 | May 28, 2026 | Completed | May 28, 2026
2.2 | PLAN | Define Tasks & Sequences | Tasks identified: connect HappyFox API → pull tickets → pass to Claude → display TLDR → UI polish (links, fonts, bullet spacing, Duration field). | May 22, 2026 | May 28, 2026 | Completed | May 28, 2026
2.3 | PLAN | Estimate Effort & Duration | Iterative build approach; no fixed timeline — developed session by session via Claude Code. | May 22, 2026 | May 28, 2026 | Completed | May 28, 2026
2.4 | PLAN | Assign Roles (RACI) | Ashley: Responsible & Accountable for all tasks. Claude Code: Consulted for dev implementation. Agents: Informed as end users. | May 22, 2026 | May 22, 2026 | Completed | May 22, 2026
2.5 | PLAN | Develop the Schedule | No fixed milestone dates; continuous sprint model — changes tested and deployed per session. | May 22, 2026 | May 30, 2026 | Completed | May 30, 2026
2.6 | PLAN | Plan Resources & Budget | Resources: Claude Code (Claude Pro plan), HappyFox API key, local machine. Budget issue identified Jun 4: accidental $19.64 API charge resolved by switching back to Pro subscription. | May 22, 2026 | Jun 4, 2026 | Completed | Jun 4, 2026
2.7 | PLAN | Identify Risks | Risks identified: Claude Code auth issues on Windows (materialized), API billing vs. Pro plan confusion (materialized), Streamlit server dependency. | May 30, 2026 | Jun 4, 2026 | Completed | Jun 4, 2026
2.8 | PLAN | Plan Risk Responses | Mitigated: Claude Code login issue fixed via API key env variable → later resolved by deleting API key and re-logging into Claude Pro. Streamlit vs HTML evaluated May 31. | May 30, 2026 | Jun 4, 2026 | Completed | Jun 4, 2026
2.9 | PLAN | Define Communication Plan | Weekly operational report (WE 0530) references this project. Status shared with team via Linksys Ops reporting cadence. | May 30, 2026 | May 30, 2026 | Completed | May 30, 2026
2.10 | PLAN | Get Plan Approved | Ashley self-approved as project owner; project pinned in Claude Code confirming go-ahead. | May 22, 2026 | May 22, 2026 | Completed | May 22, 2026
3.1 | EXECUTE | Hold Project Kickoff Meeting | Solo project — no formal kickoff. Work began immediately in Claude Code on May 22. | May 22, 2026 | May 22, 2026 | Completed | May 22, 2026
3.2 | EXECUTE | Manage Team Performance | Solo execution. Progress tracked through Claude Code session history and WE operational reports. | May 22, 2026 | Jun 5, 2026 | In Progress
3.3 | EXECUTE | Execute Work Packages | Completed: HappyFox API integration, Claude summarization, UI changes (remove links in tables, Duration fix, font → sans-serif, bullet spacing, removed Raw Ticket JSON section). | May 22, 2026 | Jun 5, 2026 | In Progress
3.4 | EXECUTE | Conduct Quality Assurance | Manual QA through live testing on localhost:8501. Issues found and fixed iteratively during Claude Code sessions. | May 22, 2026 | Jun 5, 2026 | In Progress
3.5 | EXECUTE | Manage Stakeholder Engagement | Project reported in WE 0530 operational report as one of three active Claude Projects. Team aware of tool development. | May 30, 2026 | May 30, 2026 | In Progress
3.6 | EXECUTE | Manage Procurement | No vendors. Tools used: Claude Code (included in Pro plan), HappyFox API (existing). | May 22, 2026 | May 22, 2026 | Completed | May 22, 2026
4.1 | MONITOR | Track Progress vs. Plan | Progress tracked via Claude Code session history and operational weekly reports. Latest check Jun 5 — app could not be accessed (Streamlit server not running). | May 22, 2026 | Jun 5, 2026 | In Progress
4.2 | MONITOR | Monitor Budget vs. Actuals | Budget incident Jun 4: $19.64 charged via API billing (Claude Code logged in with wrong method). Resolved by deleting API key and re-authenticating under Claude Pro subscription. | Jun 4, 2026 | Jun 4, 2026 | Completed | Jun 4, 2026
4.3 | MONITOR | Conduct Status Meetings | Reviewed in May 29 operations dashboard meeting covering filters, CSAT, Channel Performance, and reporting output format (Excel/PDF). | May 29, 2026 | May 29, 2026 | In Progress
4.4 | MONITOR | Manage Issues & Escalations | Issues logged: (1) Claude Code auth on Windows — fixed. (2) 1M context/Usage Credits error on Pro plan — fixed via /model command. (3) $19.64 API charge — resolved. | May 30, 2026 | Jun 4, 2026 | In Progress
4.5 | MONITOR | Monitor & Update Risk Register | New risk identified Jun 5: Streamlit server dependency (app inaccessible when server not running). Evaluation of HTML migration still open. | May 31, 2026 | Jun 5, 2026 | In Progress
4.6 | MONITOR | Manage Change Requests | Change evaluated May 31: Streamlit vs plain HTML/index.html. Pros/cons documented. Decision pending. | May 31, 2026 | Jun 5, 2026 | In Progress
4.7 | MONITOR | Adjust Plan as Needed | Pending decision on Streamlit → HTML migration. Plan to be updated once architecture decision is made. | Jun 5, 2026 | Jun 5, 2026 | In Progress
5.1 | CLOSE | Verify Deliverable Completion | App not yet closed — still in active development and iteration. |  |  | Not Started
5.2 | CLOSE | Obtain Formal Acceptance | Pending — will require sign-off once feature-complete. |  |  | Not Started
5.3 | CLOSE | Transition to Operations | Pending — Streamlit or HTML version to be handed off to team for daily use. |  |  | Not Started
5.4 | CLOSE | Conduct Lessons Learned Session | Planned — key learnings include Claude Code billing setup, Windows auth issues, and Streamlit server dependency risks. |  |  | Not Started
5.5 | CLOSE | Archive Project Documentation | Pending — Claude Code session history and operational reports serve as current documentation. |  |  | Not Started
5.6 | CLOSE | Release Team & Resources | N/A — solo project. |  |  | Not Started
5.7 | CLOSE | Write Final Project Report | Pending — to summarize ticket volume impact, agent time savings, and budget spend. |  |  | Not Started
5.8 | CLOSE | Celebrate & Recognize the Team | Pending — Ashley to acknowledge own effort and team impact once project is complete! 🎉 |  |  | Not Started