## Session Summary
WE (Week Ending) | What We Did | Challenges | Fix | Test Ticket(s) | Next Steps
2026-05-25 | Created Streamlit app with HappyFox API integration Built Claude AI analysis pipeline (structured JSON output) Set up PostgreSQL DB (metaboard) with caching Built HTML report generator with download/open/print Created View Saved Reports page with token cost tracking Pushed initial commit to GitHub | HappyFox API returns updates in two different formats (embedded vs endpoint) with different field names | Built dual-format parser that checks both structures and normalizes to a common format | #29640 - MX4200 (early test, no updates) #130211 - MX6200 (early test, no updates) #129157 - FGW5500 (early test, no updates) #129347 - MX6200 (early test, no updates) #128936 - FGMM1000 (early test, no updates) #130546 - MX4200 Overload (19-25 updates, tested 4x) #129512 - MBE7000 (72 updates) #120920 - LN1400/MBE7000 (122-126 updates) #13054 - Chat conversation (9 updates) | Design QA scoring system Expand Claude prompt for deeper analysis
2026-05-25 |  | API credentials must not be committed to git | Used Streamlit's built-in secrets.toml system and added it to .gitignore
2026-05-29 | Continued testing with more ticket types Tested non-English tickets (Spanish) Tested high-update-count tickets (100+ updates) Refined prompt and output formatting | Large tickets with 100+ updates hit token limits and took longer to process | Monitored token usage per ticket; prioritised caching to avoid repeat API costs | #130381 - FGW5500 (28 updates) #129640 - E8450 WiFi (56 updates) #131007 - FGW5500 (13 updates) #121534 - FGW5500 (246 updates - largest) #26188 - Un nodo sin conexion (7 updates, Spanish) #126188 - MBE7002 Wired Disconnection (193 updates) #109928 - FGW5500 (96 updates) | Build QA scoring system Add agent-level analysis
2026-06-07 | Tested with IPOE connection ticket Validated prompt against complex multi-agent ticket (152 updates) | Ticket #127911 with 152 updates and 21K input tokens - highest token usage so far | Caching ensures repeat views cost nothing; tracked token usage in saved reports page | #127911 - LN6001 IPOE connection error (152 updates, 21K input tokens) | Redesign Claude prompt for QA scoring
2026-06-14 | Redesigned Claude prompt (Senior QA Analyst + Linksys Technician + CX Director) Built dual scoring system (1-5): Technical Accuracy & Customer Handling per agent Added Agent Scorecard table with roles, scores, flags, summaries Added Coaching Notes (agent, finding, correct script, policy ref) Added Coaching Priority Banner (URGENT / REVIEW / GOOD) Added Technical QA Findings, Soft Skill Findings, Opportunities sections Built delete_cache.py utility Expanded JSON output to 30+ fields Created feature branch and opened PR #1 | Claude returned scores as strings instead of integers, breaking scorecard rendering | Added isinstance type checking for score comparisons and color-coding logic | #131976 - MX6201 (56 updates) #132182 - MX6201 (47 updates) | Implement Gemini audit recommendations Build premature close detection
2026-06-14 |  | Agent names appeared as full email addresses (e.g., jorgenathaniel.amores@concentrix.com) | Built _clean_agent_name() helper to strip @concentrix.com and @linksys.com domains
2026-06-14 |  | Anthropic API credits drained to $19.64 unexpectedly | Discovered Claude Code CLI defaulting to Opus model. Locked app to claude-sonnet-4-6
2026-06-16 | Analysed Gemini Internal Auditing Memorandum (ticket #127492) Built Premature Close Detection (Observe and Close KPI trap) Built Callback Breach Tracking (promise vs actual follow-up) Built Complex Environment Checklist (5 checks for 4+ node mesh) Built session-grouped Detailed Case Summary with colored dots and inline flags Reorganized UI into two-tab layout (Summary + Deep Dive) Added auto-translation via deep-translator Built 4 Plotly visualizations (Dot Timeline, Sankey, Donut, Swimlane) Built HTML report equivalents for all new sections Fixed report opening via base64 Blob URL | Plotly Sankey rejected 8-digit hex colors (#d9770680) | Built _hex_rgba() helper to convert to rgba(r,g,b,alpha) format | #131478 - MR8300 slow speed (55 updates) #118250 - MX5500 separate 2.4GHz (20 updates) #132712 - FGW5500 (59 updates) #127492 - MX4200 No internet (170 updates) - primary QA test ticket | Add Actions Taken section Fix Agent Scorecard cache bug
2026-06-16 |  | Opening HTML report broke when it contained Plotly script tags | Switched to base64-encoding HTML, creating Blob URL, opening in new tab
2026-06-16 |  | Dot Timeline clustered all entries on same date - unreadable | Used entry index (#1, #2...) on X axis instead of actual dates
2026-06-16 |  | What Happened section was flat dump of 50+ raw updates with email addresses | Built build_session_groups() to group by date gaps and key events, with session titles and cleaned names
2026-06-16 |  | Non-English messages (Spanish, Filipino) not readable by supervisors | Added _auto_translate() using deep-translator GoogleTranslator (triggers when >30% non-ASCII)
2026-06-18 | Added Actions Taken section (collapsed expander, [Agent / Date] format) Discovered Agent Scorecard cache bug - #127492 has empty agents_involved Investigated DB and confirmed empty ai_json Identified short test tickets (#133821, #133824, #133827 - 2 msgs each, ~$0.02) Created session handoff system with passphrase resume | Agent Scorecard stopped appearing - cached ai_json has empty agents_involved array | Need to delete cached row with delete_cache.py and re-analyse ticket | #127492 - MX4200 (cache investigation, scorecard bug) Identified for next test: #133821 - Dropping connection (2 msgs, ~$0.02) #133824 - Router default name (2 msgs, ~$0.02) #133827 - Product features inquiry (2 msgs, ~$0.02) | Test Actions Taken with short ticket (#133821) Clear cache and re-run #127492 for scorecard Sync HTML report layout to match two-tab UI Commit June 18 changes to git
2026-06-18 |  | Re-running #127492 is expensive (large ticket, many updates) | Queried HappyFox API for short tickets. Found 2-message tickets costing ~$0.02 vs $0.10+